## Attendance log
SAFETY IN DESIGN WORKSHOP ATTENDANCE
|  | Workshop #1 | Workshop #2 | Workshop #3 | Workshop #4
Name | Role
|  | Date | Date | Date | Date

## Change log
Date | Completed by | Changes (update, workshop, etc) | Comments

## Risk Register
Safety in Desgin Risk Template
Consulant | [5 empty] | Replace this text with the engineering firm(s) |  | Last edit date |  | Project Name
Ref # | Source | R = Risk O = Opportunity | Status Open or Closed | Risk Location | Risk Category | Project Section | Discipline | Life Cycle Phase | Safety in Design Hazard/Issue | Cause | Consequences | Responsibility | Existing Controls (Implementation Commenced or Complete) | Existing Control Owner | Safety | Assets | Financial | Environmental | Regulatory | Reputational | Budget | Performance | Schedule | Max Current Consequence | Current Likelihood | Current Level of Risk | Planned Future Controls (Planned but implementation not yet commenced) | Action Owner | By When | Residual Consequence | Residual Likelihood | Residual Level of Risk | Comments | Current Risk Level Score | Comments | Residual Likelihood (%) | Minimum (P10) Residual Cost | Basis for Minimum (P10) Residual Cost | Most Likely Cost | Basis for Most Likely Cost | Maximum (P90) Residual Cost | Basis for Maximum (P90) Residual Cost | Probability Distribution Adopted | Unplanned Risk | Occur? | Unplanned Total= Pert X Likelihood | #NAME? | at | au | av | Safety | Assets | Financial | Environmental | Regulatory | Reputational | Budget | Performance | Schedule | Max Current Consequence | bg | nh | Safety | Assets | Financial | Environmental | Regulatory | Reputational | Budget | Performance | Schedule
|  | R | Open | [20 empty] | #N/A |  | NA | [5 empty] | NA |  | #N/A | [9 empty] | #NAME? | #NAME? | [14 empty] | 0 |  | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | R | Open | [20 empty] | #N/A |  | NA | [5 empty] | NA |  | #N/A | [9 empty] | #NAME? | #NAME? | [14 empty] | 0 |  | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | R | Open | [20 empty] | #N/A |  | NA | [5 empty] | NA |  | #N/A | [9 empty] | #NAME? | #NAME? | [14 empty] | 0 |  | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | R | Open | [20 empty] | #N/A |  | NA | [5 empty] | NA |  | #N/A | [9 empty] | #NAME? | #NAME? | [14 empty] | 0 |  | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | R | Open | [20 empty] | #N/A |  | NA | [5 empty] | NA |  | #N/A | [9 empty] | #NAME? | #NAME? | [14 empty] | 0 |  | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | R | Open | [20 empty] | #N/A |  | NA | [5 empty] | NA |  | #N/A | [9 empty] | #NAME? | #NAME? | [14 empty] | 0 |  | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | R | Open | [20 empty] | #N/A |  | NA | [5 empty] | NA |  | #N/A | [9 empty] | #NAME? | #NAME? | [14 empty] | 0 |  | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | R | Open | [20 empty] | #N/A |  | NA | [5 empty] | NA |  | #N/A | [9 empty] | #NAME? | #NAME? | [14 empty] | 0 |  | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | R | Open | [20 empty] | #N/A |  | NA | [5 empty] | NA |  | #N/A | [9 empty] | #NAME? | #NAME? | [14 empty] | 0 |  | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA
|  | R | Open | [20 empty] | #N/A |  | NA | [5 empty] | NA |  | #N/A | [9 empty] | #NAME? | #NAME? | [14 empty] | 0 |  | FALSE | NA | NA | NA | NA | NA | NA | NA | NA | NA
If additional rows are required, then insert them above the bottom row of the current table and copy the formula and formatting into the new row(s) by copying an existing blank row. | [25 empty] | NA
|  | R | Open | [18 empty] | Moderate |  | Moderate | Likely | R H-3B |  |  |  | Moderate | Likely | R H-3B |  | 175 | [9 empty] | #NAME? | #NAME? | [12 empty] | 7 |  | 7 |  | TRUE | NA | NA | NA | NA | NA | NA | NA | R H-3B | NA
Note on G5: To facilitate importing this register into the master register we need the section name to be repreated in each row.

## IR Risk Matrices
Inland Rail Risk Classification
Risk Category |  |  |  | Consequence
|  |  |  | Not Significant | Minor | Moderate | Major | Extreme
Safety category is focussed on Impact to People |  | S: Safety |  | No Medical Treatment Required | Lost Time Injury (LTI) Results OR Medical Treatment Required | Serious Injury Occurs | Single Fatality Occurs | Multiple but Localised Fatalities Occur
Asset category is focussed on Operations Impact, Track, Systems (Hardware & Software) and Human Assets |  | A: Assets |  | Up to 6hrs Track Closure | >6hrs to 24hrs Track Closure | >24hrs to 48hrs Track Closure | >48hrs to 5 Days Track Closure | >5 Days Track Closure
Focussed on Financial Impact Cash flow, liquidity, Capital, Asset Value, Procurement & Contracts related exposure [to ARTC at the General ledger not Programme/project level] |  | F: Financial | Note 1 | Up to $250k | >$250k to $2M | >$2M to $10M | >$10M to $50M | >$50M
Focussed on Environment Impact Heritage, Flora & Fauna, Archaeology & Indigenous, Pollution and Amenity (Public) |  | E: Environment |  | Contained Environmental Damage - fully recoverable (no cost or ARTC action required) | Isolated Environmental Damage - minimal ARTC remediation required | Localised/Clustered Environmental Damage - requiring remediation | Considerable Environmental Damage - requiring remediation | Widespread Long Term or Permanent Environmental Damage - remediation required
Focussed on Regulatory/Legislation Exposure Non-compliance & Our Licence to Operate |  | R: Regulatory |  | Minimal or no Regulatory Involvement | Notice to Produce Information | Improvement Notice or Threatened Action | Prohibition Notice or Fine(s) | Prosecution of the Company and/or its Office Holders
Focussed on Reputational Exposure Customer Dissatisfaction, Shareholder Support, Service Quality & Reliability, Public Image and Stakeholder Attitudes |  | R: Reputation |  | Isolated event able to be resolved (up to 7 days) | Management intervention required (>7 days to 3 months) | Tactical (Business Unit/ Divisional) intervention required (>3months to 18 months) | Strategic intervention required (>18 months to 3 years) | Corporate loss of Shareholder and/or Customer support (tangible business impact >3 years)
Focused on Total Outturn Cost Impact to the programme and/or project [not ARTC general ledger] |  | B: Budget | Note 1 Note 2 | Up to 0.05% of programme budget (ie to $5M in $10B) | >0.05% to 0.5% of programme budget (ie>$5M to $50M in $10B) | >0.5% to 1.5% of programme budget (ie>$50M to $150M in $10B) | >1.5% to 5% of programme budget (ie>$150M to $500M in $10B) | >5% of programme budget (ie>$500M in $10B)
|  |  | Note 2 | Up to 0.1% of project budget (eg to $100k in $100M) | >0.1% to 0.5% of project budget (eg >$100k-$500k in $100M) | >0.5% to 2.5% of project budget (eg >$500k-$2.5M in $100M) | >2.5% to 10% of project budget (eg >$2.5M-$10M in $100M) | >10% of project budget (eg >$10M in $100M)
Focused on engineering impact(s) and satisfying programme/project objectives. |  | P: Performance |  | Minor impact on a programme/ project objective | Minor impact on more than one programme/ project objective | Significant impact on a programme/ project objective | Severe impact on a programme/ project objective or significant impact on more than one objective | Severe impact on more than one programme/ project objective
Focused on time based impacts to the programme and/or project |  | S: Schedule | Note 2 Note 3 | Influences schedule up to 1% of programme approved schedule period (ie up to 30 days over 10 year schedule) | Influences schedule >1% to 2.5% of programme approved schedule period (ie >30-75 days over 10 year schedule) | Influences schedule >2.5% to 5% of programme approved schedule period (ie >75-150 days over 10 year schedule) | Influences schedule >5% to 10% of programme approved schedule period (ie >150-300 days over 10 year schedule) | Influences schedule >10% of programme approved schedule period (ie >300 days over 10 year schedule)
|  |  | Note 3 | Influences schedule up to 2% of project approved schedule period (ie up to 6 days/schedule year) | Influences schedule >2% to 5% of project approved schedule period (ie >6-15 days/schedule year) | Influences schedule >5% to 10% of project approved schedule period (ie >15-30 days/schedule year) | Influences schedule >10% to 20% of project approved schedule period (ie >30-60 days/schedule year) | Influences schedule >20% of project approved schedule period (ie >60 days/schedule year)
Note 1: Financial impact relates to impact on ARTC's General Ledger (profitability). Budget impact relates to project cost outcome. A budget impact may not result in a Financial impact if project cost change is met by other parties. Note 2: Where project risk analysis is undertaken for a single phase of a project then budget and schedule values should be for that phase only. Note 3: Example schedule impacts based on nominal work calendar of 6 days/week, 50 weeks/year, ie 300 days/year.
Indicative Project Schedule Duration Range: |  |  | Indicative Project Budget Range:
| Phase duration (years) |  | $50M-$1200M | $50M | $1200M
Development | 2 |  | 0.1% | 50000 | 1200000
Tender & award | 0.5 |  | 0.5% | 250000 | 6000000
Detail design | 0.5 |  | 2.5% | 1250000 | 30000000
Construction | 1.75-5.25 |  | 10% | 5000000 | 120000000
Commissioning | 0.5
TOTAL | 5.25-8.75
Consequence
|  |  |  | Descriptor | Not Significant | Minor | Moderate | Major | Extreme
Likelihood |  |  |  | Level | 1 | 2 | 3 | 4 | 5
Description | Frequency of Occurrence | Percentile | Descriptor
Is expected to occur in most circumstances | Once per month | >90% | Almost Certain | A | MED - 1A | MED - 2A | HIGH - 3A | V HIGH - 4A | V HIGH - 5A
Will probably occur in most circumstances | Between once a month and once a year | 60%-90% | Likely | B | LOW - 1B | MED - 2B | HIGH - 3B | V HIGH - 4B | V HIGH - 5B
Might occur at some time | Between once a year and once in five years | 30%-<60% | Possible | C | LOW - 1C | LOW - 2C | MED - 3C | HIGH - 4C | HIGH - 5C
Could occur at some time | Between once in 5 years and once in 20 years | 10%-<30% | Unlikely | D | LOW - 1D | LOW - 2D | LOW - 3D | MED - 4D | MED - 5D
May occur in exceptional circumstances | Once in more than 20 years | <10% | Rare | E | LOW - 1E | LOW - 2E | LOW - 3E | LOW - 4E | MED - 5E

## Lookups (hidden)
Sections |  | Disciplines |  | Phases - EGP-20-01
Tottenham to Albury | T2A | Programme / Project | B | Concept
Albury to Illabo | A2I | Buildings | C | Feasibility
Illabo to Stockinbingal | I2S | Civil - Rail | E | Assessment
Stockinbingal to Parkes | S2P | Civil - Road | M | Approval
Parkes to Narromine | P2N | Environmental & Investigations | S | Implementation
Narromine to Narrabri | N2N | Rail Systems | T | Close-out
Narabri to North Star | N2NS | Structures
Noirth Star to NSW/Bld Borber | N2B | Tunnels
NSW/QLd border to Gowrie | B2G
Gowrie to Helidon | G2H
Helidon to Calvert | H2C
Calvert to Kagaru | C2K
Kagaru to Acacia Ridge | K2AC

## Do not Modify (hidden)
|  | Safety | Assets | Financial | Environment | Regulatory | Reputation | Budget | Performance | Schedule
|  | Extreme | Major | Moderate | Minor | Not Significant
|  | Almost Certain | Likely | Possible | Unlikely | Rare |  |  |  |  | R VH-5A | 3600 | Tottenham to Albury
[11 empty] | R VH-5B | 1500 | Albury to Illabo
[11 empty] | R H-5C | 300 | Illabo to Stockinbingal
[11 empty] | R M-5D | 120 | Stockinbingal to Parkes
|  |  | 1 | 2 | 7 | 30 | 60 |  |  |  | R M-5E | 60 | Parkes to Narromine
|  |  | Not Significant | Minor | Moderate | Major | Extreme |  |  |  | R VH-4A | 1800 | Narromine to Narrabri
| 60 | Almost Certain | 60 | 120 | 420 | 1800 | 3600 |  |  |  | R VH-4B | 750 | Narrabri to North Star
| 25 | Likely | 25 | 50 | 175 | 750 | 1500 |  |  |  | R H-4C | 150 | Moree Bypass
| 5 | Possible | 5 | 10 | 35 | 150 | 300 |  |  |  | R M-4D | 60 | Parkes Bypass
| 2 | Unlikely | 2 | 4 | 14 | 60 | 120 |  |  |  | R L-4E | 30 | North Star to NSW Border
| 1 | Rare | 1 | 2 | 7 | 30 | 60 |  |  |  | R H-3A | 420 | NSW Border to Gowrie
[11 empty] | R H-3B | 175 | Gowrie to Helidon
[11 empty] | R M-3C | 35 | Helidon to Calvert
|  |  | Consequences | [7 empty] | R L-3D | 14 | Calvert to Kagaru
[11 empty] | R L-3E | 7 | Kagaru to Acacia Ridge
|  |  | Not Significant | Minor | Moderate | Major | Extreme |  |  |  | R M-2A | 120 | Acacia Ridge to Port of Brisbane
Likelihood |  | Almost Certain | M-1A | M-2A | H-3A | VH-4A | VH-5A |  |  |  | R M-2B | 50 | Early Works
|  | Likely | L-1B | M-2B | H-3B | VH-4B | VH-5B |  |  |  | R L-2C | 10 | Programme
|  | Possible | L-1C | L-2C | M-3C | H-4C | H-5C |  |  |  | R L-2D | 4 | Corporate
|  | Unlikely | L-1D | L-2D | L-3D | M-4D | M-5D |  |  |  | R L-2E | 2
|  | Rare | L-1E | L-2E | L-3E | L-4E | M-5E |  |  |  | R M-1A | 60
[11 empty] | R L-1B | 25
[11 empty] | R L-1C | 5
[11 empty] | R L-1D | 2
[11 empty] | R L-1E | 1
|  | Almost Certain | 60 |  |  |  | Extreme
|  | Extreme | 60 |  |  |  | Major
|  | Likely | 25 |  |  |  | Moderate
|  | Major | 30 |  |  |  | Minor
|  | Minor | 2 |  |  |  | Not Significant
|  | Moderate | 7
|  | Not Significant | 1
|  | Possible | 5
|  | Rare | 1
|  | Unlikely | 2
|  | 1 | Not Significant
|  | 2 | Minor
|  | 7 | Moderate
|  | 30 | Major
|  | 60 | Extreme