<Project Name>

<Stage Name>

Project Roles and Responsibilities Allocation Report

<Date Issued>

<Revision>

| Template Status |
| --- |
| Discipline: | Engineering |
| Category: | Procedure - Template |
| Related Procedure: | EGP-20-01 Project Management |
| Template number: | EGW2001T-07 Project Roles and Responsibilities Allocation |
| Date Reviewed: | 06 Jul 2015 |
| Version: | 1.2 |

Contents

1	Purpose of this Document	4

2	Project Approval Authority	4

3	Project Organisation Structure	5

4	Roles and Responsibilities	6

4.1	Job Definitions – <XXXX> Project Steering Committee	6

4.1.1	Joint Responsibilities	6

4.1.2	Approval Authority	9

4.1.3	Operational Representative (Senior User)	10

4.1.4	Job Definition – Technical Advisor (Senior Supplier)	12

4.2	Job Definitions – Project Manager and Team	14

4.2.1	Job Definition – <XXXX> Project Manager	14

4.2.2	Job Definition – Contract Manager	17

4.3	Job Definitions – Project Assurance Roles	19

Document Control

| Owner: | Australian Rail Track Corporation |
| --- | --- |
| Project: | <Project Name> |
| Document Title: | Project Roles and Responsibilities Allocation Report |
| Date Issued: | <Date Issued> |
| Revision: | <Revision> |
| Prepared by: |  |
| Purpose: |  |
| Endorsed by: |  |
| Approved by: |  |
| Date Approved: |  |
| Issued to: |  |

| Revision History |
| --- |
| Revision | Date Issued | To | Description |

# Purpose of this Document

Any Complex project should establish clear lines of responsibility and accountability for all of the people that need to be involved.

The purpose of this document is to ensure the right people are in place within the <Project Name> with the authority, responsibility and knowledge to make decisions and provide control over the project in a timely manner.

The Roles and Responsibilites allocation report will be developed at the Concept Phase of the Project and will be updated at the start of each subsequent phase to reflect the governance arangements for the next phase.

At all points it should be clear:

Who the Approval Authority is for the Project

Who the Project Manager is

Whether a Steering Commitee is required and the Steering Committee roles

The roles of all other resources on the project

The Roles and Responsibilites allocation report template should be used for all phases - only the level of detail of the content will be different as the project progresses, with more detail being introduced as the project ramps up.

# Project Approval Authority

The Approval Authority for the Concept/Feasibility/Assessment/Implementation phase of the project will be filled by:  Approval Authority Name/Group

Define and rationalise the choice of the Approval Authority for the next phase of the project. Consider:

The required financial delegations

The mission criticality and visibility of the project

The phase of the project and the authority required to effectively oversee the work in the next Phase.

In some projects the Approval Authority will be the Steering Committee itself, in others the Steering Committee may be a delegation group that represents the Approval Authority. In this case most Steering Committee decisions will require some level of external validation with the Approval Authority

If the Approval Authority is a Project Steering Committee then the next section of the document will include the Steering Committee in the organisation structure and all steering committee roles must be rationalised and described.

# Project Organisation Structure

The project organisation is shown in the following diagram.  Individual role definitions are provided for the key roles in the remainder of this document.

Amend this diagram as required to show the organisational structure.

# Roles and Responsibilities

The responsibilities for each member of the Project Management Team are described in the following sections. Each section comprises a tailored Job Description that the owner will be asked to acknowledge formally by signing and returning a copy to the <XXXX> Project Manager.

Note: It may not be appropriate in all cases to get the role incumbents to formally sign off on their roles but this step is encouraged as experience suggests that such formal acceptance of roles tends to force a real understanding and clarification of the roles at the outset.

In this template provision has been made for such signoffs.

## Job Definitions – <XXXX> Project Steering Committee

Note: If a Project Steering Committee is not appointed by the Approval Authority or EGM, the responsibilities listed below are added to those of the Approval Authority.

### Joint Responsibilities

The joint overall responsibilities of all members of the <XXXX> Steering Committee are to:

agree with the Project Manager that person's responsibilities and objectives for each phase

confirm with the Project Manager the project tolerances/flexibility in terms of cost and time for each phase

approve all major plans within known constraints

sign-off completion of each phase of work as acceptable

ensure that required resources are committed to the project

arbitrate on conflicts within the project and negotiate a solution to any problems that arise between the project and external bodies.

Approve any required scope changes and authorise the associated expenditure (via the Approval Authority where required)

Ensure the project complies with relevant ARTC strategies/directives, procedures, standards and policies

Ensure that the defined assurance roles are engaged into the project as appropriate to support the project decision making

Monitoring Project Risks

Approving changes and variations

Determining and resolving any conflicts or disputes on the project

If necessary assist Project Manager in negotiating with external bodies

Approving project closure

add any other responsibilities here as required- specific to the project

The following sections describe the specific aspects that will need to be considered at each phase of the project. The Roles and Responsibilities Allocaton Report will evolve during the project so only those roles and responsibilities relevant for each phase will be included.

Similarly as the project moves beyond each phase it may make sense to delete the roles for phases that are already completed so as to maintain the readability and relevance of the document.

At Concept Assessment

For most projects it is unlikely that the Steering Committee will be established prior to the Feasibility Phase and hence no Steering Committee role at this point.

If the Steering Committee is established to oversee the concept development then add any roles here that are relevant.

At Project Feasibility:

Validating the level and selection of the proposed project Approval Authority with ARTC Corporate Management

Define the requirements of Project Assurance and ensure that these are reflected in the governance Roles and Responsibilities Allocation Report

approve the project governance (Roles and Responsibilities Allocation Report) for Project Feasibility phase

agree with the Project Manager that person's responsibilities and objectives for the Project Feasibility phase

confirm with the Project Manager the project tolerances/flexibility in terms of cost and time for the Project Feasibility phase

commit and make available the required resources for Project Feasibility

specify any external constraints on the overall project such as time and cost.

approve the Project Feasibility Report

add any other responsibilities here as required- specific to the project

At Project Assessment:

approve the project governance for Project Assessment phase

agree with the Project Manager that person's responsibilities and objectives for the Project Assessment phase

commit and make available the required resources for Project Assessment

approve the Project Management Plan

approve the Risk Assessment and Management Plan

add any other responsibilities here as required- specific to the project

As the project progresses:

engage the defined assurance roles as required throughout the project to ensure that assurance is involved in the decision making.

promote and maintain focus on the desired project outcome

commit resources to the project as required by approved Phase/Stage Plans.

review and approve Stage Plans, Issues and Changes.

take ownership of identified project risks as allocated during plan approval.

review each completed stage and approve commencement of next stage.

authorise any changes of scope and the associated funding allocations (via the Approval Authority where required)

add any other responsibilities here as required- specific to the project

At the end of the project:

approve the End Project Documentation and ensure it is passed to the appropriate authorities.

Provide approval for implementation in conjunction with the ARTC operational areas and the Approval Authoritiy

establish arrangements for a Post-Project Review or other means for examining the actual benefits realised against those defined in the business case and Quality Plan

add any other responsibilities here as required- specific to the project

### Approval Authority

The Approval Authority’s overall responsibilities are to:

have overall responsibility for health and safety management for the project

ensure that the project Governance model (Roles and Responsibilities Allocation Report) provides appropriate involvement of all key stakeholder groups

ensure that Steering Committee meets regularly at the defined intervals

approve project expenditure within approved budget and delegation

monitor project finance on behalf of the ARTC Executive

sign off on final deliverables.

constraining user and supplier excesses

ensuring that the project gives value for money

ensure that all project, phase and stage plans meet the over-riding ARTC constraints in terms of time, cost and resources.

maintaining the project direction in accordance with the objectives.

ensure that the Steering Committee works diligently to achieve consensus on all project matters and that such consensus is acceptable to all ARTC stakeholders on the Steering Committee

ensure that the project delivers value for money to ARTC

ensure that the need of any external Approval Authority are met by facilitating approval of a range of planning, procurement and operational documents throughout the life of the project and validating such approvals where required with the Approval Authority.

ensure that all defined ARTC Resources are made available to the Project Manager

appropriately engage the defined Assurance/Advisory functions

be available to and liaise regularly with the Project Manager to ensure that the project is progressing acceptably and that the Project Manager is getting the required level of support

understand the project risk profile and approve the risk management plan

ensure that tolerances for the project are set in all plans and agreed with the Project Manager.

resolve matters of contention between the different ARTC Divisions and/or external agencies

add any other responsibilities here as required- specific to the project

I have read and agree to carry out the responsibilities contained in this job definition for Project Director

Signature:	Name: Approval Authority Name 	Date:

Title: Approval Authority Title

### Operational Representative (Senior User)

The Operational Representative is responsible for the specification of operating requirements and ensuring that what is produced is fit for purpose and within the constraints of the project objectives in terms of quality, functionality and ease of use.  The Operational Representative is a part of the Steering Committee.

Note: There may be more than one Operational Representative required on the Steering Committee as this will depend on the areas impacted by the project. Where more than one is required separate role definitions should be prepared for each role focussing on the specific elements of the role.

The Project Director may undertake the role of Operational Representative especially in the case of RCRM and MPM where there is no change to operational outcomes (e.g. an existing asset is being replaced with the same functionality). Where this occurs it is vital that the Project Director role definition in this document includes the additional responsibilities required to ensure effective operational input.

The Operational Representative (add the specific name of each discrete operational role in here so as to differentiate them) overall responsibilities are to:

ensure the desired outcome of the project is correctly and completely specified from an operational perspective;

promote and maintain focus on the desired project outcomes

resolve conflicts and prioritise operational requirements.

sign off on final deliverables.

ensure that the project adequately considers and addresses the needs of all impacted ARTC operational groups

commit all required ARTC operational resources, including project team members and assurance members, to the project (as described in this document and subsequent project plans);

ensure that the project deliverables will satisfy operational and other business requirements and are sustainable in the future;

set priorities on any proposed changes to the project specification, scope or acceptance criteria and contribute operations opinions to Steering Committee decisions on whether to implement such changes;

ensure that plans are acceptable to their operational area – specifically in relation to the time frames and resource requirements

ensure that the defined and agreed operational resources are made available from their agency

attend the Steering Committee meetings

participate in all Steering Committee approval processes as their nominated operational area Steering Committee representative

contribute operations and other relevant business expertise and opinions to Steering Committee decisions

actively involve any defined Operational Assurance roles within their agency

brief all other operations and management staff within their area on all significant matters about the project.

add any other responsibilities here as required- specific to the project

I have read and agree to carry out the responsibilities contained in this job definition for Operational Representative (add the specific name of each discrete operational role in here so as to differentiate them)

Signature:	Name: Op. Rep Name 	Date:

Title: Op. Rep. Title

### Job Definition – Technical Advisor (Senior Supplier)

The project Technical Advisor is responsible for ensuring the overall quality of the product, including that suppliers have met all requirements of Australian or international standards and technical specifications.  The Technical Advisor is a part of the Steering Committee.

Note: There may be more than one Technical Advisor required on the Steering Committee as this will depend on the technology elements of the project. For example a given project may require engineering input for the track work, safety expertise for safety management plans, signalling expertise for signalling work and IT expertise for any new or changed IT deliverables. Where more than one is required separate role definitions should be prepared for each role focussing on the specific elements of the role.

The Project Director may undertake the role of Technical Advisor although this will typically only occur on smaller projects. Where this occurs it is vital that the Project Director role definition in this document includes the additional responsibilities required to ensure effective technical input.

The Technical Advisor (add the specific name of each discrete technical role in here so as to differentiate them) overall responsibilities are to:

ensure the desired outcome of the project is correctly and completely specified from a technical perspective;

ensure that the appropriate technical resources required for the project are made available.

ensure the proposals for designing and developing the deliverables are realistic and likely to achieve the results required by ARTC within the defined cost and time parameters

ensure appropriate ARTC specialist resources are involved in the supply and development of all project deliverables, in particular to validate the technology decisions regarding the design and architecture of the solution

agree requirements for any specialist technology work and any assurance processes for the same.

ensure that the desired project time constraints can be achieved by the relevant technical area

contribute opinions to Steering Committee decisions on proposed changes by working closely with the Project Director and other Steering Committee members

Resolve technology requirements and priority conflicts involving the technology deliverables for which they are responsible

Brief and advise non-technical Steering Committee members on all significant technical matters concerning the project.

add any other responsibilities here as required- specific to the project

I have read and agree to carry out the responsibilities contained in this job definition for Operational Representative (add the specific name of each discrete technical role in here so as to differentiate them)

Signature:	Name: Tech. Advisor Name 	Date:

Title: Tech. Advisor Title

## Job Definitions – Project Manager and Team

### Job Definition – <XXXX> Project Manager

Project Manager’s Overall Responsibilities:

The Project Manager is responsible for planning and monitoring the project to ensure that the project deliverables are capable of achieving the forecast business benefits. The Project Manager must ensure the project produces the required products, to the required standard of quality and within the specified constraints of time and cost.

The general requirements of the project manager are as follows:

report to the Project Director (and the Steering Committee if relevant)

compile and present the Roles and Responsibilities Allocation Report for each phase of the project for the approval of the Project Director.

identify all WHS and rail safety responsibilities and ensure they are all assigned to a member of the project team

manage hazards and risks in construction activities and work areas

undertaking EIA and identifying environmental approvals, permits and licenses (obtaining where required) and ensure all environmental responsibilities are assigned to a member of the project team including environmental incident response

direct and motivate the project team in the work to be undertaken to deliver the project

develop all required project, phase and stage plans and other project documentation

ensure that the project produces the required products, to the required standard of quality and within the specified constraints of time and cost

facilitate all project communications and approval processes

ensure that the project produces a result that is capable of achieving the benefits stipulated in the Quality Plan

control each stage of the project, delegating technical control to the Team Managers and Team members as needed.

manage the performance of the project team

report progress to the Approval Authority according to the agreed format and frequency

formal project closure activities including the financial close out report creating the fixed asset in the ledger.

add any other responsibilities here as required- specific to the project

Project Manager’s Specific Responsibilities:

Outcome Delivery

ensure that the project remains aligned to the original concept and the outcome benefit definitions at all times

ensure that the delivery of works, systems and operational processes and procedures from the project is done in such a way as to maximise the chances of outcome and benefit delivery

add any other responsibilities here as required- specific to the project

Planning

produce the Project Management Plan

produce the project risk assessment and risk mitigation plans

agree the technical and quality strategy with appropriate members of the Steering Committee

determine the project’s resources and budget requirements and obtaining appropriate funds and resources,

prepare implementation, transition and training plans for the rollout of the capability

set clear targets and associated tolerances for production of products/deliverables by Team Managers

add any other responsibilities here as required- specific to the project

Management

set up project controls including change control and configuration management, progress capture, progress reporting and project admin activities

monitor overall progress and the use of resources, including initiation of corrective action where necessary

issue work packages to the project teams – including both suppliers and internal teams

the management, motivation and guidance of the project teams

the facilitation of the organisational change associated with the project in each of the operational areas

manage business and project risks, including the development of any contingency plans required by the Steering Committee

be accountable to the Steering Committee for overall progress and use of resources, and initiate corrective action where necessary

add any other responsibilities here as required- specific to the project

Reporting

monitoring and reporting against the agreed budget, schedule and quality baselines through Project Progress Reports (Highlight Reports) and the Steering Committee  meetings;

add any other responsibilities here as required- specific to the project

Stakeholder Management

obtain Steering Committee approval for who will undertake the defined Project Assurance roles;

continually liaise with the Steering Committee and Project Assurance roles to assure the overall direction and integrity of the project;

liaise with the relevant operational areas to ensure that necessary arrangements are made for the introduction of the new technologies and the commissioning of all new capability required by the project.

represent the project in a range of operational and technical forums and provide information regarding the project to the range of project Stakeholders - as defined in the Project Communications Management Plan.

manage user expectations across the organisation

undertake formal communications with external suppliers.

add any other responsibilities here as required- specific to the project

I have read and agree to carry out the responsibilities contained in this job definition for Project Manager

Signature:	Name: Project Manager Name

XXXX Project Manager

Date:

### Job Definition – Contract Manager

The Contract Manager is an essential role to be nominated and filled for Phases V and VI of all ARTC projects that involve procurement and the establishment of contracts with suppliers.

Often this role will be filled by the Project Manager with defined supporting assurance roles from the procurement and contract management areas of ARTC.

In other cases a specific Contract Manager role will be established for the project. The need for a separate Contract Manager will be considered during the development of the Roles and Responsibilities Allocation Report and the final decision will rest with the Steering Committee and/or the Approval Authority. This will depend on the level of project expenditure required on contracts with suppliers.

If this role is to be filled by the Project Manager then the roles and responsibilities for the Project Manager must incorporate the Contract Management Responsibilities.

If it is not the Project Manager then the Contract Manager must be clearly nominated in the contract documents and appointed in the Project Team.

Overall Responsibilities

administer the contract(s) in accordance with the contract documentation, ARTC requirements and obligations.

work closely with the Contract Administrator in order to ensure that contracts are established in accordance with ARTC’s procurement and contract management procedures and standards.

provide advice to the project manager with regard to the specification, issue and evaluation of tenders

provide advice to the project manager with regard to the specification, negotiation and execution of all supplier contracts

make any required procurement and/or contract management resources available to the project as defined within the project, phase and stage plans.

assist with the identification and management of procurement and contract related risks.

fulfil all WHS and rail safety responsibilities assigned.

add any other responsibilities here as required- specific to the contract and procurement work required on the <XXXX> project.

I have read and agree to carry out the responsibilities contained in this job definition for Contract Manager <XXXX>

Signature:	Name: Contract Manager Name

XXXX Contract Manager

Date:

#### Job Definition – Team Leader <YYYY>

The project Team Leader <YYYY> is responsible for ensuring the <YYYY> project team designs develops/acquires the defined products to the required quality specification and within the cost and time constraints agreed with the project manager.

Note: There will usually be more than one Team Leader required on the project - this will depend on the breadth of the deliverables to be produced by the project. For example a given project may require team leaders to oversee the track work, a signalling upgrade and  new or changed IT deliverables. In this case it is likely that three distinct Team Leader roles will be required. Where more than one is required, separate role definitions should be prepared for each Team Leader role focussing on the specific elements of the role.

In smaller projects team leader roles may not be required or the Project Manager may undertake one or more of these roles.

The Team Leader <YYYY> (add the specific name of each discrete team leader role in here so as to differentiate them) overall responsibilities are to:

make workplaces safe

prepare plans for team’s work and agree these with the Project Manager

direct, motivate and monitor a work team

expedite information required by team members from the Project Manager or others as required

monitor progress of the work team and initiate corrective action where necessary.

advise the Project Manager of any major deviations from the team plan, recommended corrective actions, and help prepare Exception Report.

ensure that quality control within the work team is planned and performed correctly.

manage work team risks.

prepare a Team Plan

prepare regular Team Status Reports at the required frequency (Note it may be more relevant to include the provision of progress updates to the Project Manager as written team leader reports may not be appropriate on all projects)

add any other responsibilities here as required- specific to the team leader role required to oversee the specific work packages for which the team is responsible. This should make clear the range of deliverables for which the Team Leader is responsible.

I have read and agree to carry out the responsibilities contained in this job definition for Project Team Leader <YYYY>

Signature:	Name: Project Leader Name

YYYY Project Team Leader

Date:

## Job Definitions – Project Assurance Roles

The <XXXX> project requires a range of advisory or assurance roles in order to improve the quality of the decision making made by the Steering Committee and to ensure that decisions are taken with full insight into the operational, organisational and technical implications.

The key advisory roles are described in this section.

Note: The project assurance roles are essential if the project is going to get real input from the full range of stakeholders.

For each Steering Committee member the following questions should be asked:

What will the Steering Committee member require advice on in the course of the next phase of the project?

Which particular deliverable approvals or other decisions will require the advice?

When is this going to be required?

Who is best placed to provide this advice?

How is the input best received e.g. by reviewing draft documents and providing advice to the Steering Committee member; via formal meetings or verbally at key stages?

Formal assurance roles are not required for all projects - In smaller projects there will typically be less need for the roles.

The Project Assurance <ZZZZ> (add the specific name of each discrete assurance role in here so as to differentiate them) overall responsibilities are to:

Provide advice to (add the Steering Committee role here who will receive the advice) on the following aspects of the project)

operational advice on the appropriateness of proposed designs, solutions or change of operational practice

technical advice on technology selection or the validity of the proposed solutions

assurance that a proposed solution can be sustained operationally and technically

procurement approaches

contract structure and management

any organisational change management elements

quality assurance on the project execution and processes such as project management processes, risk management, quality management, testing etc

anything else that the Steering Committee or other key stakeholders need independent advice on.

I have read and agree to carry out the responsibilities contained in this job definition for <Project Assurance Role Name>

Signature:	Name:

Project Assurance Role Name

Date: